## Sheet1
Task 1
Start Date | Duration | Finish Date | Defining Scope and Objectives
Duration:
5 days
|  |  | Start Date | End Date
|  |  | 2023-10-05 | 2023-10-10

## Sheet3
Defining Scope and Objectives
Duration:
2
Start Date |  | End Date
2023-10-20 |  | 2023-10-22
User Requirements Analysis
Duration:
2
Start Date |  | End Date
2023-10-22 |  | 2023-10-24
System Analysis
Duration:
1
Start Date |  | End Date
2023-10-24 |  | 2023-10-25
Web Scraping Module
Duration:
5
Start Date |  | End Date
2023-10-25 |  | 2023-10-30
Data Processing Module
Duration:
2
Start Date |  | End Date
2023-10-30 |  | 2023-11-01
Django Framework and Interface
Duration:
1
Start Date |  | End Date
2023-11-01 |  | 2023-11-02
Django Framework and Interface
Duration:
1
Start Date |  | End Date
2023-11-02 |  | 2023-11-03
Error Handling
Duration:
1
Start Date |  | End Date
2023-11-03 |  | 2023-11-04
Documentation
Duration:
4
Start Date |  | End Date
2023-11-04 |  | 2023-11-08
Implementation
Duration:
1
Start Date |  | End Date
2023-11-08 |  | 2023-11-09
User/Manual Testing
Duration:
1
Start Date |  | End Date
2023-11-09 |  | 2023-11-10
Error Handling
Duration:
4
Start Date |  | End Date
2023-11-10 |  | 2023-11-14
Technical Documentation
Duration:
3
Start Date |  | End Date
2023-11-14 |  | 2023-11-17
Start
End